## (1) Q1_Components
Sl. | Components | Type
1 | Multi-agents based on prompt templates built with Google ADK | Agent
2 | Agent with instructions, tools and config parameters | Agent
3 | Session caching with Redis | Caching
4 | Tool and Semantic cache | Caching
5 | Session restoration with Firestore (definitely in GA) | Caching
6 | Session single source of truth on GCS | Memory
7 | Session retrieval from GCS with Firestore componsite index ( potentially in GA) | Memory
8 | Pub/Sub for session restoration and archival | Memory
9 | Logging - 3 types | Monitoring
10 | Model callbacks/Cloud Traces integration for monitoring | Monitoring
11 | Transactiong analytics on BQ | Monitoring
12 | Cloud Run for daily analytics into BigQuery | Monitoring
13 | Cloud Scheduler for daily analytics | Monitoring
14 | Load balancer | Networking
15 | API Gateway/APIGEE | Networking
16 | Authentication with existing tech | Security
17 | Cloud Armor for WAF and DDoS | Security
18 | Model callbacks for safety guardrails | Safety
19 | Model Armor for safety guardrails (potentially in GA) | Safety
20 | Cloud Run for agent deployment | Deployment
21 | CICD pipelines | Deployment
22 | Data adapter layer | Data
23 | Core banking system encapsulated via Adapter layer | Data
Architectural assumption: - Chat UI can be standalone or embedded in existing application. The subsequent flow and components have been considered. - Google ADK is deployed with Cloud Run and existing bank authentication is used to authenticate users.
Other teams and systems: - Core banking application and team - Existing bank security method and security team - Architecture, Networking, Application support, Cloud Engg teams - CAB and business

## (2) Q2_Q3_PhaseSummary
Sl. | Phase | Comments
1 | MVP | As this phase is to prove the concept and value, it will focus on providing functionality safely to users. Focus will be on adhering to org security standards and less so for archival, full-on session restoration, throughput etc.
2 | GA | If MVP is successful, effort will be spent on delivering a fully resilient solution that will be optimised for speed, restoration, cost etc.
3 | Go criteria | 1) Full compliance with org's security requirements 2) Full adherence to safety guardrails for agent and tool output 3) Seamless user experience for bot's responses 4) Viability in terms of token/cloud costs

## (3) Q4_SprintGoals
Phase | Sprint | Activities | Deliverables
MVP | 1 | 1) Requirement gathering and Workflow design with process re-engineering 2) Define MVP architecture - cloud services, security, logging, memory management, latency 3) Agent structuring, design and development of mock agents 4) Environment set up for solution development 5) Design for BQ schema, GCS structure, JSON schema and data pipelines 6) Design for authentication/authorisation | 1) Requirements 2) Solution/Workflow/Agent design 2) Architecture for approval 3) Contract between systems for handshaking 4) DEV environment
MVP | 2 | 1) Agent development with context engineering, session caching in Redis and Logging 2) Feedback from business through demos 3) APIGEE configuration 4) Implementation of Data Adapter Layer | 1) Initial version of Agentic solution 2) Feedback from business for refinement 3) Manually deployed solution with Cloud Run
MVP | 3 | 1) User testing and solution enhancement with bug fixing and additional features that may be required 2) Integration with Core Banking API 3) Implementation of security requirements - Load Balancer, Cloud Armor, JWT, IAM hardening, Secret Manager etc. | 1) UAT feedback 2) Core banking integration with org security standards.
MVP | 4 | 1) Implementation of Callbacks for guardrails & monitoring, Transaction analytics data in BigQuery, Pub/Sub configuration and Archival of chat transcript in GCS | 1) Fully implemented MVP
MVP | 5 | 1) System integration testing, Penetration testing, UAT and bug fixing 2) Development of CICD pipelines and Terraform scripting for IaaS | 1) Completed testing 2) P1/P2/P3 bug fixes 3) CICD pipelines
MVP | 6 | 1) Release planning and approval 2) E2E deployment dry run in PRE-PROD 3) Controlled deployment | 1) MVP Release plan 2) Successful dry run 3) MVP release to PROD
GA | 7 | 1) Generation of metrics from BigQuery for analytics 2) Introspection of metrics, raising of bugs and plan to fix | 1) Insights from Live 2) Enhancement plan
GA | 8 | 1) Load/Stress testing of solution to decide on Firestore for session recovery and wider adoption 2) Bug fixes and prioritised feature enhancements | 1) Load testing results and priorities 2) MVP bugs and feature enhancements fully implemented
GA | 9 | 1) Implementation of full caching, composite index in Firestore for GCS and enhanced security with Model Armor | 1) UAT ready solution
GA | 10 | 1) UAT and business sign-off for Go Live | 1) Deployment ready solution 2) Business sign-off
GA | 11 | 1) Plan for GA Release and ELS 2) Security compliance audits and approval, CAB approval for Go-live | 1) Release plan with ELS process 2) All approvals in place for GA release
GA | 12 | 1) Phased rollout 2) Hypercare operations | 1) Phase rollout with ELS

## (4) Q5_RiskMitigation
Sl. | Risk | Mitigation
1 | Lack of clarity on workflow may mismatch with user expectation and lead to agent re-engineering | Early view to help visually experience the solution
2 | Lack of enterprise level architectural patterns can delay technology choice and architecture | Early engagement with Arch team
3 | Lack inadequate support from Core banking team can delay the integration | Appropriate estimation of time and early engagement
4 | Security flaws identified late in the development cycle | Front loading security implementation to allow sufficient time for validation
5 | High latency and LLM cost | Adequate caching, skills implementation and cost monitoring from early stages of development
6 | Inconsistent response from agent | Prioritising determinsm in otucome and tightening all prompts with business review